Whitfield Carter LLP

Solicitors

22 Bishopsgate, London EC2N 4BQ  •  DX 122 London  •  +44 (0)20 7946 0000  •  www.whitfieldcarter.com

PROJECT DRAKE

Series B Financing — Completion Checklist

Matter: Aldermore Robotics Limited — Series B Subscription (WC-00114)

Target Completion: 31 October 2025

Prepared by: Elena Marchetti, Whitfield Carter LLP

| # | Document / Step | Responsibility | Status |
| --- | --- | --- | --- |
| 1 | Mutual NDA executed | WC / Hargrove | Complete (11 Jul) |
| 2 | Term Sheet signed | WC / Westgate | Complete (24 Jul) |
| 3 | Legal, financial & tax due diligence | Westgate / Marlow Tax | Complete |
| 4 | Subscription Agreement agreed (v3 settled) | WC / Hargrove | Agreed (08 Oct) |
| 5 | Investor Rights Agreement agreed | WC / Hargrove | Agreed |
| 6 | New Articles of Association in agreed form | WC | Agreed |
| 7 | Disclosure Letter and data room index finalised | WC / Company | Complete |
| 8 | Cap table (pre/post) reconciled to consideration | WC / Company | Reconciled |
| 9 | Shareholders' written resolutions (adopt Articles; allotment authority; s.561 disapplication) | Company | To sign at Completion |
| 10 | Board minutes approving Transaction Documents and allotment | Company | To sign at Completion |
| 11 | Subscription monies (£18.0m) to WC client account | Investors | On Completion |
| 12 | Allot Series B Shares; update register of members; issue certificates | Company / WC | On Completion |
| 13 | Appoint Investor Director (Daniel Westbrook); note observer | Company | On Completion |
| 14 | File SH01, AP01 and new Articles at Companies House | WC | Within 15 days |
| 15 | Funds flow executed; net proceeds released to Company | WC | On Completion |
| 16 | Bible / closing set circulated | WC | Post-Completion |

Note: Items 9–13, 15 to be dealt with simultaneously at the virtual Completion on 31 October 2025; post-Completion filings to follow within statutory time limits.