Project Quartz — Completion Checklist

Completion target: 12 December 2025

Prepared by: Elena Marchetti, Whitfield Carter LLP — version of 9 December 2025

| # | Document / Step | Responsible | Status |
| --- | --- | --- | --- |
| 1 | Patent Licence Agreement (execution version) finalised | WC / Denham Lewis | Agreed 8 Dec |
| 2 | Side letter finalised | WC | Agreed 8 Dec |
| 3 | Aldridge board approval (minutes) | Aldridge / WC | Passed 10 Dec |
| 4 | Brandt management approval (Geschäftsführung resolution) | Brandt / Denham Lewis | Confirmed 9 Dec |
| 5 | Schedule 1 patent particulars verified with Hartington IP | Hartington IP | Confirmed 5 Dec |
| 6 | Technical package (Schedule 2) ready for delivery | Aldridge (Dr Tindall) | Ready |
| 7 | Execution copies circulated for e-signature | WC | Circulated 11 Dec |
| 8 | Upfront fee £1,250,000 — payment instructions issued | Aldridge / Brandt | Issued 11 Dec |
| 9 | Receipt of upfront fee confirmed | Aldridge | On completion |
| 10 | Exchange of signed counterparts; release | WC / Denham Lewis | On completion |
| 11 | Conformed copies and bible distributed | WC | Post-completion |
| 12 | Patent register note of exclusive licence (optional) | Hartington IP | Post-completion |

Notes: Completion to occur by exchange of e-signed PDF counterparts under clause 14 of the Licence. The licence is not conditional; the upfront fee is payable within 10 business days of completion but the parties have agreed to remit on the completion date.