## Action Plan
Maple Court Care Home — Remedial Action Plan Tracker
Ashbourne Healthcare Group Limited · Matter WC-00189 · Re: CQC Warning Notice (Reg 12) & Notice of Proposal · Compliance date: 30 April 2025
Status as at 12 May 2025. Prepared with Whitfield Carter LLP. PRIVILEGED & CONFIDENTIAL.
Ref | Finding / required action | Regulation | Owner | Target date | Status | % complete | Evidence reference
A1 | Implement electronic medicines administration (eMAR) system across all four units | Reg 12 | Clinical Lead / IT | 2025-04-22 | Complete | 100% | eMAR go-live confirmation 22/04/25
A2 | 100% audit of high-risk medicines (anticoagulants, insulin, opioids) — replace sampling audit | Reg 12 | Registered Manager | 2025-03-31 | Complete | 100% | Revised audit SOP v3; April audit log
A3 | Medicines competency reassessment of all nurses (substantive and agency) | Reg 12 | Clinical Lead | 2025-04-18 | Complete | 100% | Competency matrix 18/04/25
A4 | Fill substantive night-nurse vacancy on Ferndale unit | Reg 18 | HR / COO | 2025-04-14 | Complete | 100% | Contract start 14/04/25
A5 | Commission external medicines audit by independent pharmacist | Reg 17 | Quality Director | 2025-04-28 | Complete | 100% | External audit report 28/04/25
A6 | Daily MAR reconciliation check by nurse-in-charge, signed off | Reg 12 | Nurse in Charge | 2025-03-17 | Complete | 100% | Daily check sheets (ongoing)
A7 | Duty of candour meeting with resident's family; written apology | Reg 20 | Registered Manager | 2025-02-10 | Complete | 100% | Candour log; letter 10/02/25
A8 | Monthly medicines-governance report to CQC | Reg 17 | Quality Director | 2025-03-31 | Complete | 100% | March & April reports submitted
A9 | Fortnightly quality-assurance visits by Group quality team | Reg 17 | Quality Director | 2025-03-24 | Complete | 100% | QA visit logs
A10 | Appoint dedicated clinical lead for Maple Court | Reg 18 | COO | 2025-05-06 | Complete | 100% | Appointment 06/05/25
A11 | Registered manager additional medicines-governance training | Reg 18 | Registered Manager | 2025-05-09 | Complete | 100% | Training certificate 09/05/25
A12 | Refresh safeguarding & escalation procedure; staff briefing | Reg 13 | Registered Manager | 2025-05-16 | In progress | 80% | Draft procedure; briefing scheduled
A13 | Resident & family reassurance forum | Reg 17 | Registered Manager | 2025-05-23 | In progress | 50% | Forum invitations issued
| Overall completion (weighted average of actions) |  |  |  |  | 94.62%
| Actions complete / total |  |  |  |  | 11 / 13

## Cost Summary
Maple Court Remediation — Indicative Cost Summary (£)
Internal estimate for board reporting. Excl. VAT. Source: Group Finance, May 2025.
Item | One-off cost (£) | Annualised cost (£) | Notes
eMAR system (licences + hardware) | 18500 | 9600 | 3-year licence; hardware one-off
Substantive night nurse (Ferndale) | 0 | 46800 | Replaces agency spend
Dedicated clinical lead (0.6 WTE) | 0 | 38400 | New post
External medicines audit (independent pharmacist) | 4200 | 4200 | Quarterly thereafter
Staff medicines training & competency | 3100 | 1500 | Refresher annually
Legal & regulatory advice (Whitfield Carter LLP) | 42000 | 0 | Estimate to representations stage
Quality-assurance visit programme | 0 | 7200 | Group quality team time
Total | 67800 | 107700
Year-1 total impact (one-off + annualised) | 175500