## Disclosure Index
BRACKEN GROUP PLC v CALDERWOOD INDUSTRIES LIMITED — Claim No. CL-2025-000412
EXTENDED DISCLOSURE — CLAIMANT'S DISCLOSURE LIST (Model C, PD 57AD). Date: 27 March 2026
Doc ID | Date | Description | Type | Author / From | Recipient / To | Issue(s) | Privilege / Status
BRK-0001 | 14/03/2023 | Supply Agreement (executed) between Bracken Group plc and Calderwood Industries Ltd | Agreement | Bracken / Calderwood | — | 1,2,3 | Disclosed
BRK-0002 | 14/03/2023 | Specification SP-HPX-440 rev. C (technical schedule) | Specification | Bracken Engineering | Calderwood | 2 | Disclosed
BRK-0003 | 10/03/2023 | Tender evaluation and supplier selection record (HPX-440) | Record | Bracken Procurement | Internal | 1 | Disclosed
BRK-0004 | Apr–Jun 2024 | Rolling 12-week forecasts issued to Calderwood (Q2 2024) | Forecast | Bracken Procurement | Calderwood | 4 | Disclosed
BRK-0005 | 18/07/2024 | Site-meeting note, Sheffield (Doyle / Hartley) | Note | Bracken Operations | Internal | 5 | Disclosed
BRK-0006 | 02/08/2024 | Incoming QA test report — batch B-2408 (pressure failure) | QA report | Bracken QA | Internal | 2 | Disclosed
BRK-0007 | 16/08/2024 | Incoming QA test report — batch B-2411 (pressure failure) | QA report | Bracken QA | Internal | 2 | Disclosed
BRK-0008 | 21/08/2024 | Email Calloway to Doyle re non-conforming deliveries | Email | R. Calloway | G. Doyle | 2,5 | Disclosed
BRK-0009 | 27/08/2024 | Email Doyle to Calloway (response) | Email | G. Doyle | R. Calloway | 2,5 | Disclosed
BRK-0010 | 09/09/2024 | Email Calloway to Doyle (chaser) re pressure failures | Email | R. Calloway | G. Doyle | 2 | Disclosed
BRK-0011 | 13/09/2024 | Incoming QA test report — batch B-2419 (pressure failure) | QA report | Bracken QA | Internal | 2 | Disclosed
BRK-0012 | 03/10/2024 | Email Calloway to Doyle re continuing failures and delays | Email | R. Calloway | G. Doyle | 2,3 | Disclosed
BRK-0013 | 18/10/2024 | Call-off order CO-2024-188 (undelivered) | Order | Bracken Procurement | Calderwood | 3 | Disclosed
BRK-0014 | 16/10/2024 | Email Doyle to Calloway re sub-contractor fire / delays | Email | G. Doyle | R. Calloway | 3,6 | Disclosed
BRK-0015 | 12/11/2024 | Call-off order CO-2024-201 (undelivered) | Order | Bracken Procurement | Calderwood | 3 | Disclosed
BRK-0016 | Sep 2024–Feb 2025 | Production downtime logs, Sheffield line | Records | Bracken Operations | Internal | 3,7 | Disclosed
BRK-0017 | Sep 2024–Feb 2025 | Goods-inwards rejection register (HPX-440) | Register | Bracken QA | Internal | 2,8 | Disclosed
BRK-0018 | 28/02/2025 | Termination letter Bracken to Calderwood | Letter | Bracken Group plc | Calderwood | 6 | Disclosed
BRK-0019 | 05/03/2025 | Calderwood reply to termination (reservation of rights) | Letter | Calderwood | Bracken | 6 | Disclosed
BRK-0020 | 11/03/2025 | Marlin Hydraulics Ltd supply quotation and price schedule | Quotation | Marlin Hydraulics | Bracken | 7,8 | Disclosed
BRK-0021 | Mar 2025 | Competing quotations obtained for replacement supply | Quotations | Various suppliers | Bracken | 8 | Disclosed
BRK-0022 | 2025 (various) | Marlin Hydraulics invoices (replacement supply) | Invoices | Marlin Hydraulics | Bracken | 7 | Disclosed
BRK-0023 | Mar 2025–Feb 2026 | Bracken purchase ledger extract (replacement supply) | Records | Bracken Finance | Internal | 7 | Disclosed
BRK-0024 | Sep 2024–Feb 2025 | Contribution / margin analysis, HPX-440 product line | Analysis | Bracken Finance | Internal | 7 | Disclosed
BRK-0025 | 2024–2025 | Rework, scrap and quarantine cost records (batches B-2408+) | Records | Bracken Operations | Internal | 7 | Disclosed
BRK-0026 | 09/12/2025 | Defence (Calderwood) | Pleading | Pemberton Rowe | Court / WC | all | Disclosed
BRK-0027 | 20/01/2026 | Advice on merits and quantum, C. Rosenthal KC | Advice | Counsel | Bracken / WC | all | Withheld — legal advice privilege
BRK-0028 | various | Correspondence Whitfield Carter / Bracken re strategy | Email | Whitfield Carter | Bracken | all | Withheld — legal advice privilege
BRK-0029 | 21/05/2026 | Draft witness statement of R. Calloway (working drafts) | Statement | R. Calloway / WC | Internal | all | Withheld — litigation privilege
BRK-0030 | 2025–2026 | Instructions to and draft report of forensic accountant | Report | WC / expert | Internal | 7 | Withheld — litigation privilege
Total documents listed:
Disclosed:
Withheld for privilege: