Bracken v Marldon — Chronology (working document, privileged)

Claim No. HT-2026-000214. Prepared by Whitfield Carter LLP. Last updated 6 May 2026.

| Date | Event | Source / ref |
| --- | --- | --- |
| 09 Jan 2024 | Bracken issues enquiry data pack (effluent chemistry, loading, flow) to three suppliers | BG-ENQ-01 |
| 22 Jan 2024 | Marldon site survey; Mr Hartley attends | Site survey note |
| 28 Feb 2024 | Marldon quotation MQ-4471 Rev C issued (price £1,480,000) | MQ-4471 Rev C |
| 14 Mar 2024 | Contract formed: PO BG-PROC-2271 accepted on Marldon standard terms | PO BG-PROC-2271 |
| Sep 2024 | System delivered to site | Delivery note DN-2271 |
| 04 Nov 2024 | 30-day performance demonstration test commences — fails from outset | Commissioning logs |
| Dec 2024 | Morrow raises pump elastomer concern with Marldon engineer | WS T Morrow §6 |
| Nov 2024–Aug 2025 | Eleven separate System failure events; lines shut down | Site failure register RE1 |
| Mar 2025 | Worst outage: Line 2 down 9 days | Failure register |
| 12 Sep 2025 | Bracken accepts repudiatory breach; terminates Contract | Termination letter |
| Sep 2025 | Severnvale Water Technologies engaged for replacement system | Severnvale order |
| 07 Nov 2025 | Letter before action sent to Marldon | LBA 07/11/2025 |
| 05 Dec 2025 | Marldon letter of response (denies liability) | Marldon LoR |
| Jan 2026 | Replacement system commissioned and operating | Severnvale commissioning cert |
| 06 Feb 2026 | Particulars of Claim filed (HT-2026-000214) | POC Filed |
| 18 Mar 2026 | Defence served | Defence |
| 19 Mar 2026 | First CMC; directions order made | CMC Order 19/03/2026 |
| 22 Apr 2026 | Reply served | Reply |
| 08 May 2026 | Marldon Part 36 offer (£450,000) | Part 36 letter |