## Schedule of Loss
Bracken Coatings & Surface Technologies Limited v Marldon Process Systems Limited
Claim No. HT-2026-000214 — SCHEDULE OF LOSS — as at 6 February 2026 (prepared by Whitfield Carter LLP)
Item | Head of loss | Description / basis | Qty | Unit | Unit cost (£) | Amount (£)
1. Remedial works to System
| Membrane module replacement (interim) | Replacement UF modules during failure period | 4 | set | 38500 | 154000
| Permeate pump rebuilds / reseals | Six pump interventions, parts & labour | 6 | event | 9800 | 58800
| Emergency tankering of untreated effluent | Licensed disposal during outages | 1180 | m3 | 165 | 194700
| Bracken engineering labour (remedial) | Internal labour at standard rate | 1640 | hr | 78 | 127920
| Third-party process support | External process engineer call-outs | 1 | sum | 106580 | 106580
| Subtotal — Remedial works |  |  |  |  | 642000
2. Replacement treatment system
| Severnvale MBR system - design & supply | Replacement turnkey system | 1 | sum | 712000 | 712000
| Installation & commissioning | Severnvale install contract | 1 | sum | 158000 | 158000
| Civils & tie-in works | Groundworks and pipework modifications | 1 | sum | 45000 | 45000
| Subtotal — Replacement system |  |  |  |  | 915000
3. Lost production
| Line 1 downtime | Lost contribution, recorded outage hours x margin | 612 | hr | 410 | 250920
| Line 2 downtime | Lost contribution incl. 9-day March outage | 742 | hr | 410 | 304220
| Expedited/cover production premium | Overtime & subcontracted coating to meet orders | 1 | sum | 2860 | 2860
| Subtotal — Lost production |  |  |  |  | 558000
4. Investigation costs
| Independent process engineer report | Root-cause investigation | 1 | sum | 34000 | 34000
| Effluent sampling & laboratory analysis | COD/TSS testing programme | 1 | sum | 16000 | 16000
| Subtotal — Investigation costs |  |  |  |  | 50000
| TOTAL CLAIM (excl. interest) |  |  |  |  | 2165000
Interest (s.35A SCA 1981) — to be assessed
Note: Heads 1 and 4 are evidenced by third-party invoices; head 3 is calculated from line-output records and standard contribution margins.