# Remediation and Improvement Plan

Calverton Industries Limited — Wednesbury plant. Project Lyra (HSE ref WM/SAN/2026/0488). In response to Improvement Notice I/WM/2026/0488/01.

## 1. Objective

To ensure that thread-rolling and other rotating work equipment at the Wednesbury plant is so guarded and interlocked that access to dangerous parts while in motion is prevented, and to put in place an effective system to prevent the defeat of guard interlocks, in compliance with PUWER 1998 regulations 11 and 22 and the Improvement Notice.

## 2. Workstreams and actions

| Ref | Action | Owner | Target date |
| --- | --- | --- | --- |
| A1 | Take all four Excelon EX-class cells out of service until retrofitted | Neil Tasker | Completed 19 Mar 2026 |
| A2 | Recover all interlock actuator keys; introduce controlled key issue register | Neil Tasker | Completed 20 Mar 2026 |
| A3 | Retrofit trapped-key interlocks and dual-channel guard monitoring (4 cells) | OEM / Engineering | 31 May 2026 |
| A4 | Commission fresh PUWER suitability assessments for all rotating cells | External assessor | 24 May 2026 |
| A5 | Re-write safe system of work for clearing mis-rolls; mandatory lock-off | Neil Tasker | 30 Apr 2026 |
| A6 | Refresher training: isolation, lock-off, guard integrity (all operators) | HR / SHEQ | 15 Jun 2026 |
| A7 | Plant-wide guarding review of all rotating equipment | SHEQ | 30 Jun 2026 |
| A8 | Supervisor briefing: zero tolerance of guard defeat; reporting duty | Operations | 30 Apr 2026 |

## 3. Governance

Progress will be reviewed fortnightly by the Site Safety Committee, chaired by the Operations Director, with Neil Tasker reporting. A completion report will be provided to the HSE by 1 June 2026 and evidence retained for each action.

## 4. Verification

Each retrofitted cell will be re-commissioned only after a documented PUWER suitability assessment and a sign-off by the SHEQ Manager. The new safe system of work will be verified by supervised observation over the first two weeks of operation.