SCHEDULE 1

STATEMENT OF WORK (IMPLEMENTATION & SERVICES)

to the Master Software-as-a-Service Agreement between Caspian Technologies Limited (Supplier) and Stratton Energy plc (Customer)

1.  Scope of the Services

1.1	The Supplier shall provide the Customer with access to the Caspian Climate Intelligence Platform (Enterprise tier) and the implementation, configuration, data-integration, training and support services described in this Schedule, to enable the Customer to measure, manage and report its Scope 1, Scope 2 and Scope 3 greenhouse-gas emissions across its UK and European operations and to prepare related regulatory and voluntary disclosures.

1.2	The Enterprise tier comprises the emissions-measurement, analytics, target-setting, supplier-engagement and disclosure-reporting modules, together with the application programming interfaces necessary to ingest activity data from the Customer’s source systems.

1.3	Capitalised terms used but not defined in this Schedule have the meanings given in the Agreement.

2.  Implementation phases, deliverables and milestones

The implementation shall be delivered in the following phases, commencing on 1 June 2026 and targeting a Go-Live Date of 1 July 2026:

| Phase | Description | Key deliverables | Target |
| --- | --- | --- | --- |
| 1. Mobilisation | Project kick-off, governance set-up, data-source mapping and project plan baseline | Project initiation document; RACI; data-source inventory | Wk 1–2 |
| 2. Configuration | Tenant set-up, emissions factors library, organisation hierarchy, single sign-on (SSO) and role configuration | Configured tenant; SSO live; emissions-factor set signed off | Wk 3–5 |
| 3. Data integration | Connect ERP, utility, fuel-card and business-travel data feeds via API and secure file transfer | Up to 8 source-system integrations; data-validation report | Wk 4–7 |
| 4. UAT & training | User-acceptance testing against the test script; training of Authorised Users; cutover plan | Signed UAT acceptance certificate; trained user cohort | Wk 8–9 |
| 5. Go-Live & hypercare | Production go-live and two weeks’ enhanced hypercare support | Go-Live confirmation; hypercare exit report | 1 Jul 2026 |

2.1	Acceptance: the Customer shall test each deliverable against the agreed acceptance criteria within five Business Days of delivery. A deliverable is deemed accepted if the Customer does not provide written notice of non-conformity within that period. The Go-Live Date occurs on the Supplier’s written confirmation following the Customer’s sign-off of the UAT acceptance certificate.

3.  Authorised Users and onboarding scope

3.1	The Services support up to 250 named Authorised Users. The Implementation and Onboarding Fee of £85,000 (clause 6.1 of the Agreement) covers tenant configuration, integration of up to eight source systems, migration of up to 24 months of historic activity data, and instructor-led training of up to 40 users across two cohorts.

3.2	Onboarding deliverables beyond this scope (for example, additional source-system integrations or bespoke report templates) shall be treated as professional services under paragraph 4.

4.  Professional services

4.1	Additional professional services requested by the Customer beyond the implementation scope shall be charged at £1,250 per consultant-day, drawn down under work orders agreed in writing. The parties estimate 40 consultant-days in year 1 (£50,000), which is an estimate and not a commitment.

4.2	Each work order shall record the scope, estimated effort, deliverables, acceptance criteria and any assumptions. Travel and out-of-pocket expenses are chargeable at cost where pre-approved in writing by the Customer.

5.  Governance

5.1	The parties shall hold a fortnightly project board during implementation and quarterly business reviews after Go-Live. Each party shall nominate a project sponsor and a project manager as its day-to-day points of contact.

6.  Customer responsibilities and dependencies

6.1	The Customer shall: (a) provide timely and complete access to the relevant source systems and activity data; (b) nominate a project sponsor and project manager; (c) procure the participation of relevant business and IT personnel for workshops, UAT and training; and (d) provide decisions and approvals within five Business Days of request.

6.2	Delays attributable to the Customer’s failure to meet a dependency shall entitle the Supplier to a reasonable extension of the affected milestones and to recover reasonable additional costs incurred as a result.

7.  Charges summary

| Item | Basis | Amount |
| --- | --- | --- |
| Annual Subscription Fee (Year 1) | Per annum, in advance | £450,000 |
| Implementation & Onboarding Fee | One-off, on signature | £85,000 |
| Professional services (Year 1 est.) | 40 days @ £1,250/day | £50,000 |
| Estimated total Year 1 charges |  | £585,000 |

Confidential and may be legally privileged.