PROJECT INDIGO

COMPLETION CHECKLIST

Patent and Know-How Licence — Cobalt Photonics / Tessandri Instruments

Target completion: 16 February 2026

| No. | Document / Step | Responsible | Status |
| --- | --- | --- | --- |
| 1 | Mutual NDA (executed) | WC / Castle counsel | Complete |
| 2 | Term Sheet signed | Parties | Complete |
| 3 | IP ownership & encumbrance review | T. Gallagher (WC) | Complete |
| 4 | Freedom-to-operate opinion (Hartington IP) | Hartington IP | Complete |
| 5 | Patent and Know-How Licence Agreement — final form | E. Marchetti (WC) | Agreed |
| 6 | Disclosure Letter | Cobalt / WC | Agreed |
| 7 | Cobalt board approval (minutes) | Cobalt | Complete |
| 8 | Tessandri board approval | Tessandri | Complete |
| 9 | Schedule 1 (Patent Schedule) finalised | Hartington IP / WC | Complete |
| 10 | Technology-transfer plan (Schedule 2) agreed | Cobalt CTO | Complete |
| 11 | Execution of Licence Agreement (counterparts) | Parties | At completion |
| 12 | Payment of first upfront instalment (£2,000,000) | Tessandri | At completion |
| 13 | Registration of licence at relevant patent offices | Hartington IP | Post-completion |

Prepared by Whitfield Carter LLP. This checklist is for working purposes only and does not vary the terms of the Licence Agreement.