COMPLETION CHECKLIST

Acquisition of Calderdale House, 14–18 Sefton Street, Manchester M3 4AP

Buyer: Ellwood Estates Partners Limited   |   Matter ref: WC-00165 (SW/EM/Calderdale)

Target completion: 28 March 2025

## A.  Pre-exchange

| # | Item | Responsible | Status |
| --- | --- | --- | --- |
| A1 | AML / source of funds verification complete | WC – Elena Marchetti | Done 06 Feb |
| A2 | Report on title approved by client | WC / Client | Done 24 Feb |
| A3 | Searches received and clear (local, drainage, environmental, chancel) | WC | Done 18 Feb |
| A4 | Replies to CPSE enquiries reviewed | WC | Done 14 Feb |
| A5 | Building survey received (Calderbank Vine) | Client / WC | Done 21 Feb |
| A6 | Contract approved – final form agreed (v3) | WC / Pemberton Rowe | Done 05 Mar |
| A7 | Buyer board resolution authorising purchase | Client | Done 04 Mar |
| A8 | Deposit funds (£845,000) cleared in WC client account | Client / WC | Done 06 Mar |

## B.  Exchange of contracts

| # | Item | Responsible | Status |
| --- | --- | --- | --- |
| B1 | Contracts dated and exchanged (telephone, Law Society formula B) | WC / Pemberton Rowe | Done 07 Mar |
| B2 | Deposit (10% = £845,000) sent to Seller’s solicitors as stakeholder | WC | Done 07 Mar |
| B3 | Buyer’s VAT option to tax notified to HMRC; acknowledgement obtained | WC / Client | Done 12 Mar |

## C.  Pre-completion

| # | Item | Responsible | Status |
| --- | --- | --- | --- |
| C1 | TR1 transfer approved and engrossed | WC / Pemberton Rowe | Done 18 Mar |
| C2 | Completion statement agreed (apportionments) | WC / Pemberton Rowe | Open |
| C3 | OS1 priority search and bankruptcy/company search | WC | Open |
| C4 | Funds requisition to client for completion balance | WC | Open |
| C5 | Tenant notices of assignment of reversion prepared | WC | Open |

## D.  Completion and post-completion

| # | Item | Responsible | Status |
| --- | --- | --- | --- |
| D1 | Completion monies transferred; transfer dated | WC | — |
| D2 | Rent deposit (Castleford, £29,250) transferred to Buyer | Pemberton Rowe / WC | — |
| D3 | SDLT return submitted and SDLT paid | WC | — |
| D4 | Application to register transfer at HM Land Registry (AP1) | WC | — |
| D5 | Notices of assignment served on the three tenants | WC | — |
| D6 | Original documents and completed file to client | WC | — |