## Schedule of Loss
HALSTEAD AEROSPACE LIMITED v FERNCLIFFE ALLOYS LIMITED
Claim No. HT-2025-000612 — Schedule of Loss and Damage (Annexed to Particulars of Claim)
Technology and Construction Court, Business and Property Courts of England and Wales — Prepared 11 March 2025
KEY QUANTITIES & RATES (inputs)
| Non-conforming bar delivered (Heats FA-7733 & FA-7741) | 4280 | kg
| Contract price of bar (per kg) | 96.5 | £/kg
| Finished wing-rib fittings scrapped (CM-7 programme) | 312 | units
| Machining / conversion value added per scrapped fitting (excl. raw material) | 4570 | £/unit
| Expedited replacement bar premium over contract price | 38 | £/kg
| Replacement bar required (incl. test coupons & yield loss) | 4690 | kg
| Line-stop / under-recovery of fixed overhead (days) | 14 | days
| Line-stop day rate (Bay 4, CM-7 cell) | 21500 | £/day
No. | Head of loss | Qty | Unit | Rate (£) | Amount (£) | Basis / cross-reference
1 | Scrapped wing-rib fittings — machining / conversion value | 312 | units | 4570 | 1425840 | 312 fittings; conversion value added only (raw bar at head 2); QN-2024-0337
2 | Scrapped non-conforming raw bar (Heats FA-7733/FA-7741) | 4280 | kg | 96.5 | 413020 | Bar rejected on incoming + in-process test; AMS 4928 fail
3 | Expedited replacement bar — price premium | 4690 | kg | 38 | 178220 | Northvale Metals spot order; premium over Ferncliffe price
4 | Line-stop / fixed-overhead under-recovery (Bay 4) | 14 | days | 21500 | 301000 | 14 working days; Ops log; CM-7 cell idle
5 | Liquidated damages exposure — late CM-7 shipset deliveries to Caldera | 1 | lump | 412000 | 412000 | Caldera MSA LDs at 0.5%/wk; 3 shipsets slipped
6 | Additional metallurgical testing & failure investigation | 1 | lump | 84600 | 84600 | Argent Metallurgical Services invoices A-1180/1206/1241
7 | Re-inspection & 100% lot screening of remaining stock | 1 | lump | 47350 | 47350 | NDT + chemical re-test of 11 retained heats
8 | Internal management & engineering time (CARB / RCCA) | 1 | lump | 36800 | 36800 | Time records; 412 hours @ blended £89.32
9 | Expedited inbound freight & customs (replacement bar) | 1 | lump | 18240 | 18240 | Air freight DAP Bristol; broker invoices
| Sub-total — direct losses |  |  |  | 2917070
| Interest to date (s.35A Senior Courts Act 1981 — 4.0% from 30 Sep 2024) |  |  |  | 52747
| TOTAL CLAIMED (excluding costs) |  |  |  | 2969817
Note: Head 1 captures only the machining/conversion value added to the scrapped fittings; the raw-material cost of the bar consumed in them is claimed separately at head 2, so there is no double recovery. Figures exclude VAT (recoverable) and legal costs (to be assessed).