## Schedule of Loss
Harrow Precision Engineering Limited v Brevdale Castings Limited
Claim No. HT-2025-000418 ¦ Amended Schedule of Loss (rev 2, 28 January 2025)
Prepared by Whitfield Carter LLP. All figures exclusive of VAT and of interest under s.35A Senior Courts Act 1981.
Head 1 — Replacement conforming castings
Item | Part no. | Qty | Unit cost (£) | Cost (£) | Notes
Replacement housing castings (large) | HPE-PH-340 | 430 | 580 | 249400 | Alt foundry; premium over Brevdale price
Replacement housing castings (small) | HPE-PH-220 | 1000 | 112 | 112000 | Alt foundry
Expedited tooling / pattern hire | — | 1 | 36800 | 36800 | One-off pattern refurbishment
|  |  | Sub-total Head 1 | 398200
Head 2 — Rework, strip-down and field recall
Item | Part no. | Qty | Unit cost (£) | Cost (£) | Notes
Strip & rebuild — units in stock (labour) | — | 92 | 640 | 58880 | 6.4 hrs/unit @ £100
Field recall — units returned from customers | — | 286 | 1180 | 337480 | Recall logistics + rebuild; 286 units
Replacement seals, gaskets & fasteners | — | 378 | 140 | 52920 | Consumables per rebuilt unit
Recall programme management & comms | — | 1 | 199620 | 199620 | Project overhead, helpline & customer mgmt
|  |  | Sub-total Head 2 | 648900
Head 3 — Carriage, inspection and disposal
Item | Part no. | Qty | Unit cost (£) | Cost (£) | Notes
Independent radiographic inspection | — | 1 | 41200 | 41200 | Wraysbury & in-line NDT
Carriage — returns and replacements | — | 1 | 28850 | 28850 | Inbound/outbound freight
Scrap handling & disposal of defective castings | — | 1 | 16000 | 16000 | Licensed metal disposal
|  |  | Sub-total Head 3 | 86050
Head 4 — Liability to Stratton Energy plc (downstream)
Item | Part no. | Qty | Unit cost (£) | Cost (£) | Notes
Liquidated damages — late/defective supply | — | 1 | 275000 | 275000 | Framework contract cl. 11; 0.5%/wk capped
Contractual rebate triggered on quality breach | — | 1 | 150000 | 150000 | Framework contract sch. 4
|  |  | Sub-total Head 4 | 425000
|  |  | TOTAL CLAIM (amended) | 1558150
|  |  | Original total (pre-amendment, 11 Feb 2025) | 1421650
|  |  | Increase on amendment (extended recall to 286 units) | 136500