## Schedule of Loss
HARTWELL PHARMA LIMITED v TESSARACT BIOREAGENTS LIMITED
Claim No. CL-2026-000118 — Schedule of Loss (served with Particulars of Claim, 16 January 2026; updated 6 March 2026)
All figures in £ sterling, exclusive of VAT and interest. Sources: Hartwell cost ledger; OOS-2025-037; supplier invoices.
Ref | Head of loss | Description / basis | Qty / basis | Unit rate (£) | Amount (£)
1 | Wasted manufacturing & analytical costs — lot DP-2025-114
1.1 | API consumed in failed lot (batch TX-HX218-0461, 3.2 kg) |  | 3.2 | 78500 | 251200
1.2 | GMP manufacturing suite occupancy & labour (campaign 1) |  | 22 | 24600 | 541200
1.3 | In-process & release analytical testing (failed lot) |  | 1 | 196400 | 196400
1.4 | Stability chamber allocation & timepoints (written off) |  | 1 | 141200 | 141200
1.5 | Excipients, consumables & single-use components |  | 1 | 18900 | 18900
1.6 | Other directly-attributable campaign overheads (written off) |  | 1 | 135600 | 135600
| Subtotal — Head 1 |  |  |  | 1284500
2 | Replacement API & repeat manufacturing campaign
2.1 | Replacement API procured from alternative supplier (3.4 kg) |  | 3.4 | 92000 | 312800
2.2 | Expedited qualification & incoming testing of replacement API |  | 1 | 58400 | 58400
2.3 | Repeat GMP manufacturing campaign (campaign 2) |  | 11 | 26900 | 295900
2.4 | Repeat analytical, release & stability testing |  | 1 | 75200 | 75200
| Subtotal — Head 2 |  |  |  | 742300
3 | Clinical-site standby, re-mobilisation & study delay
3.1 | Clinical-site standby fees (7 sites x 3 months) |  | 21 | 18200 | 382200
3.2 | Re-mobilisation & re-training across sites |  | 7 | 21400 | 149800
3.3 | CRO project management — delay period |  | 4 | 46800 | 187200
3.4 | Study-delay, re-mobilisation & additional logistics |  | 1 | 239200 | 239200
| Subtotal — Head 3 |  |  |  | 958400
4 | Investigation, OOS & independent testing
4.1 | Internal OOS-2025-037 investigation (QA/QC labour) |  | 1 | 74300 | 74300
4.2 | Wraysbury Materials Laboratory independent confirmatory testing |  | 1 | 62450 | 62450
4.3 | Impurity characterisation & method work |  | 1 | 50000 | 50000
| Subtotal — Head 4 |  |  |  | 186750
| TOTAL PRINCIPAL CLAIM |  |  |  | 3171950
| Interest (s.35A Senior Courts Act 1981, to be assessed — illustrative at 8% simple from 2 Sep 2025) |  |  |  | 349697
Note: as served 16 Jan 2026, total £3,171,950. Counsel's amendment of 6 Mar 2026 uplifts Head 3 by £30,000 (extended site-standby), giving a revised principal claim of £3,201,950 pleaded in the amended Particulars.