Whitfield Carter LLP

22 Bishopsgate, London EC2N 4BQ

T +44 (0)20 7946 0118   DX 178 London/Chancery Lane

COMPLETION CHECKLIST

Project Lyra — HRX-218 Patent and Know-How Licence

Signing and Completion: 30 January 2026

Key: WC = Whitfield Carter LLP (Hartwell); BS = Birchall Stone LLP (Calderbrook); HIP = Hartington IP.

## Part A — Conditions to signing

| No. | Item | Responsibility | Status |
| --- | --- | --- | --- |
| A1 | Board approval of Hartwell to enter into the Licence (resolution / written resolution) | Hartwell / WC | Done 28 Jan |
| A2 | Board / shareholder approval of Calderbrook (incl. Aldridge Seed LP investor consent) | Calderbrook / BS | Done 29 Jan |
| A3 | Disclosure Schedule agreed and delivered | BS / WC | Done 30 Jan |
| A4 | Final FTO and chain-of-title confirmation | HIP | Done 8 Jan |

## Part B — Documents to be signed at Completion

| No. | Document | Signatories | Format |
| --- | --- | --- | --- |
| B1 | Patent and Know-How Licence Agreement (execution version) | Both parties | PDF / DocuSign |
| B2 | Deed of Release of Aldridge Seed charge over the Licensed Patents | Aldridge Seed LP / Calderbrook | Deed |
| B3 | Patent assignment recordal confirmations (chain of title) | HIP to file | EPO/USPTO forms |
| B4 | Technology-transfer plan acknowledgement | Both parties | Letter |

## Part C — Post-completion steps

| No. | Item | Responsibility | Deadline |
| --- | --- | --- | --- |
| C1 | Pay upfront fee of £6,000,000 to Calderbrook | Hartwell | 10 BD post-signing |
| C2 | Record Hartwell as exclusive licensee on the patent registers | HIP | 30 days |
| C3 | Commence technology transfer (materials, data, CMC package) | Calderbrook | 30 days |
| C4 | First Joint Steering Committee meeting | Both | 45 days |

Prepared by Whitfield Carter LLP. This checklist is a working document and is not itself a transaction document.