## Assumptions
PROJECT MERIDIAN — Sentvia Vigil™ Subscription
Commercial Model & Total Cost of Ownership (5-year view)
Whitfield Carter LLP ¦ Matter WC-00122 ¦ Prepared 28 January 2026
Key assumptions
Annual subscription (Year 1) | 486000
Implementation / migration fixed fee (one-off) | 145000
Annual uplift cap (negotiated, clause 6.6) | 5%
Authorised users (Year 1) | 120
Additional user rate (per user p.a.) | 4050
Forecast additional users from Year 2 | 15
Premium support (24x7 P1/P2) add-on p.a. | 38000
Discount applied to Year 1 subscription | 10%
VAT rate | 20%
Note: Blue cells are inputs. Annual subscription escalates at the lesser of the negotiated cap and CPI; modelled here at the cap.

## 5-Year TCO
Five-Year Total Cost of Ownership
Cost component | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Platform subscription | 437400 | 459270 | 482233.5 | 506345.175 | 531662.4337 | 2416911.1088
Additional user subscriptions | 0 | 60750 | 63787.5 | 66976.875 | 70325.7188 | 261840.0938
Premium 24x7 support add-on | 38000 | 39900 | 41895 | 43989.75 | 46189.2375 | 209973.9875
Implementation & migration (one-off) | 145000 | 0 | 0 | 0 | 0 | 145000
Subtotal (excl. VAT) | 620400 | 559920 | 587916 | 617311.8 | 648177.39 | 3033725.19
VAT | 124080 | 111984 | 117583.2 | 123462.36 | 129635.478 | 606745.038
Total (incl. VAT) | 744480 | 671904 | 705499.2 | 740774.16 | 777812.868 | 3640470.228
Contract value over 36-month initial term (subscription + implementation, excl. VAT): |  |  |  | 1523903.5

## SOW Milestones
SOW-01 Implementation — Milestone Payment Schedule
Ref | Milestone | Target date | Fee (excl. VAT) | VAT | Total
M1 | Project Initiation & Implementation Plan | 2025-12-15 | 21750 | 4350 | 26100
M2 | Environments provisioned (Prod/UAT/Sandbox) | 2026-01-09 | 21750 | 4350 | 26100
M3 | Configuration complete & spec approved | 2026-02-06 | 29000 | 5800 | 34800
M4 | Data migration dry-run & reconciliation | 2026-02-27 | 29000 | 5800 | 34800
M5 | CSV / validation pack (IQ/OQ/PQ) | 2026-03-13 | 21750 | 4350 | 26100
M6 | Go-live & hypercare | 2026-03-27 | 21750 | 4350 | 26100
| TOTAL |  | 145000 | 29000 | 174000