STATEMENT OF WORK No. SOW-01

under the Master SaaS Subscription Agreement dated [●] October 2025
between Sentvia Health Systems Limited and Hartwell Pharma Limited

# 1.  PURPOSE

This Statement of Work describes the implementation, configuration, validation and data-migration services to be provided by the Supplier to enable the Customer to adopt the Sentvia Vigil™ platform as its global pharmacovigilance case-management system. It is governed by, and incorporated into, the Master SaaS Subscription Agreement (the “Agreement”). Capitalised terms have the meanings given in the Agreement.

# 2.  SCOPE OF SERVICES

The Supplier shall provide the following work-streams: (a) project mobilisation and governance; (b) provisioning of Production, Validation and Sandbox environments; (c) configuration of intake channels, case-processing workflows, MedDRA and WHODrug dictionaries and E2B(R3) gateway routing; (d) migration of legacy case data from the Customer's incumbent Argus Safety database; (e) computer-system validation (CSV) in accordance with GAMP 5 and Annex 11, including the production of validation documentation; and (f) user-acceptance support and go-live cut-over.

# 3.  MILESTONES AND DELIVERABLES

| Ref | Deliverable | Acceptance criteria | Fee (£) |
| --- | --- | --- | --- |
| M1 | Project Initiation Document & validated Implementation Plan | Customer sign-off of PID | 21,750 |
| M2 | Environments provisioned (Prod/UAT/Sandbox) | Connectivity & access confirmed | 21,750 |
| M3 | Configuration complete; configuration specification approved | Config spec signed off | 29,000 |
| M4 | Data migration dry-run & reconciliation report | ≥99.9% record reconciliation | 29,000 |
| M5 | CSV / validation pack delivered (IQ/OQ/PQ) | Validation summary report approved | 21,750 |
| M6 | Go-live and 2-week hypercare | Production acceptance certificate | 21,750 |
|  | Total fixed fee (exclusive of VAT) |  | 145,000 |

# 4.  TIMELINE

The Supplier shall use reasonable endeavours to achieve go-live within 16 weeks of the Effective Date, in accordance with the detailed Implementation Plan to be agreed at M1. The indicative schedule is: Initiation (weeks 1–2), Configuration (weeks 3–8), Migration & validation (weeks 9–14), UAT & go-live (weeks 15–16).

# 5.  CUSTOMER RESPONSIBILITIES

The Customer shall: nominate a project sponsor and a project manager; provide timely access to source data, subject-matter experts and its quality function; review and approve deliverables within 5 Business Days of submission; and provide a validated extract of its legacy Argus database for migration. Delay by the Customer in performing these responsibilities may entitle the Supplier to a reasonable extension of the timeline.

# 6.  ACCEPTANCE

Each milestone deliverable shall be deemed accepted on the earlier of (a) the Customer's written acceptance, and (b) 5 Business Days after submission if the Customer has not provided written notice of non-conformance specifying in reasonable detail the respects in which the deliverable fails to meet its acceptance criteria. Where the Customer gives such notice, the Supplier shall correct the non-conformance and re-submit within 10 Business Days.

# 7.  CHARGES

The total fixed fee for the services described in this SOW is £145,000 (exclusive of VAT), invoiced on achievement of each milestone as set out in the table at clause 3. Any change to scope shall be handled through the change-control procedure in clause 8.

# 8.  CHANGE CONTROL

Either party may request a change to this SOW by written notice. The Supplier shall, within 5 Business Days, provide a change-impact assessment setting out the effect on scope, timeline and charges. No change shall take effect until agreed in writing and signed by an authorised representative of each party.

AGREED by the parties:

For Sentvia Health Systems Limited: ........................   Date: ............

For Hartwell Pharma Limited: ........................   Date: ............