BRAMPTON LEISURE LIMITED v HARTWELL CONSTRUCTION LTD

Claim No. HT-2025-000219

CHRONOLOGY

Prepared by Whitfield Carter LLP for the Claimant. This chronology is provided for case-management purposes and is not agreed.

| Date | Event |
| --- | --- |
| 9 Jan 2023 | JCT Design and Build Contract 2016 executed (Contract Sum £6,180,000). |
| 23 Feb 2024 | Contractual Date for Completion. |
| 8 Mar 2024 | Practical Completion certified (approx. 2 weeks late). |
| 25 Mar 2024 | The Vault Birmingham opens to members. |
| Apr 2024 | First reports of water staining to pool-hall ceiling and steelwork. |
| 10 May 2024 | Pool closed for 3 days on EHO direction (combined-chlorine breach). |
| 31 May 2024 | Membership peaks at approx. 4,180. |
| 14 Jun 2024 | Second pool closure (water-quality). |
| Jul–Aug 2024 | Studios 2 and 3 unusable; condensation and mould in pool hall. |
| 19 Aug 2024 | Third pool closure (water-quality). |
| 12 Sep 2024 | Lyle Forsyth Associates instructed to investigate. |
| 18 Oct 2024 | Lyle Forsyth Associates report delivered. |
| 14 Nov 2024 | Letter of Claim sent under the Pre-Action Protocol. |
| 12 Dec 2024 | Defendant’s Letter of Response (denies liability). |
| Dec 2024 | Membership has fallen to approx. 2,950. |
| 12 Mar 2025 | Claim Form and Particulars of Claim issued and served. |
| 9 May 2025 | Defence served. |
| 2 Jun 2025 | First Case Management Conference; directions given. |
| 26 Jun 2025 | Claimant’s witness statements exchanged. |
| Q1 2027 | Trial window (10 days, TCC). |