## Schedule of Loss
Brampton Leisure Limited v Hartwell Construction Ltd — Claim No. HT-2025-000219
CLAIMANT'S SCHEDULE OF LOSS (as at 26 June 2025)
A. Cost of remedial works
Ref | Head | Basis | Amount (£)
1.1/1.2 | Façade / roof water ingress & steelwork | LFA + structural engineer costing | 742500
2.1/2.2 | Pool water-treatment plant | M&E quantity surveyor estimate | 418000
3.1/3.2 | Pool hall ventilation & finishes | LFA + QS estimate | 596400
Sub-total A — remedial works
B. Investigation & professional fees
Ref | Item | Provider | Amount (£)
B1 | Building services & façade investigation | Lyle Forsyth Associates | 96400
B2 | Structural engineer (steelwork condition) | Calthorpe Structures Ltd | 31800
B3 | Quantity surveyor (remedial costing) | Marrable QS LLP | 38500
B4 | Water-quality / EHO liaison | Aquatec Consulting | 17500
Sub-total B — professional fees
C. Loss of profit (closures & reduced membership)
Period | Avg members | Member shortfall vs plan | Avg monthly margin/member (£) | Loss (£)
Q2 2024 (closures) | 3900 | 0 | 38 | 142000
Q3 2024 | 3450 | 600 | 38 | 263000
Q4 2024 | 3050 | 1000 | 38 | 372000
Q1 2025 | 2980 | 1050 | 38 | 366000
Q2 2025 (residual) | 3010 | 980 | 38 | 167000
Sub-total C — loss of profit
D. Member compensation & alternative provision
Ref | Item | Basis | Amount (£)
D1 | Free-month membership credits | approx. 4,100 credits @ avg £41 | 102500
D2 | Partner-gym access (pool closures) | third-party access fees | 44000
D3 | Goodwill / retention offers | discretionary retention vouchers | 22000
Sub-total D — member compensation
TOTAL CLAIM (excl. interest & costs)
Plus interest pursuant to s.35A Senior Courts Act 1981 (claimed at 4% over base) and costs, to be assessed.
Cross-check: remedial total ties to Scott Schedule (£1,756,900).