## Milestone Schedule
Project Cedar — Milestone & Payment Schedule
Larkmoor Bioscience Limited / Verrell Beauty Group plc. Per Schedule 3 & Schedule 4 of the Licence Agreement.
No. | Milestone event | Longstop date | Status | Payment (£) | Expected payment date
1 | Completion of technology transfer & pilot-scale reproduction | 6 months after Effective Date | On track | 500000 | Jul 2026
2 | Completion of regulatory / cosmetic-safety dossier (Reg. (EC) 1223/2009) | 18 months after Effective Date | Pending | 750000 | Jul 2027
3 | First commercial sale of a Licensed Product | 30 months after Effective Date | Pending | 1500000 | Jul 2028
4 | Annual Net Sales first exceeding £25,000,000 | n/a (sales-based) | Pending | 1500000 | Year 5 (est.)
| Aggregate maximum milestone payments |  |  | 4250000
| Upfront fee (Clause 7.1) |  |  | 1750000
| Total fixed consideration (upfront + milestones) |  |  | 6000000
Each milestone payment is payable once only, within 30 days of achievement of the relevant event (Schedule 4 Part B).