PROJECT MOSAIC — COMPLETION CHECKLIST

Acquisition of Cygnet House, 8 Tabard Street, London SE1 4JU · Completion 10 October 2025

This checklist tracks the documents and steps required for exchange of contracts and completion. “Who” indicates the party with primary responsibility (WC = Whitfield Carter; PR = Pemberton Rowe; Client = Marchwood).

## A.  Pre-exchange

| Item | Who | Status |
| --- | --- | --- |
| Approved engrossment of contract for sale | WC / PR | Agreed |
| Replies to CPSE.1, CPSE.4 enquiries approved | WC | Done |
| Local authority search (LLC1 / CON29) received and clear | WC | Received 12 Sep |
| Drainage and water search received and clear | WC | Done |
| Environmental search received and clear | WC | Done |
| Report on title approved by client | Client | Approved 16 Sep |
| Buyer SPV decision / nomination | Client | Buying in own name |
| AML / source of funds verification complete | WC | Done |
| Option to tax made and notified to HMRC | Client | Done 9 Sep |
| Deposit funds (£2,175,000) in WC client account | Client | Cleared 18 Sep |

## B.  Exchange of contracts (19 September 2025)

| Item | Who | Status |
| --- | --- | --- |
| Contracts exchanged by telephone (Law Society Formula B) | WC / PR | Exchanged 19 Sep |
| Deposit released to PR as stakeholder | WC | Done |
| Completion date inserted: 10 October 2025 | WC | Done |

## C.  Pre-completion

| Item | Who | Status |
| --- | --- | --- |
| Pre-completion OS1 priority search at HMLR | WC | Priority to 24 Oct |
| Company search / bankruptcy search against Seller | WC | Clear |
| Engrossed TR1 executed by Seller and held to order | PR | Held to order |
| Form DS1 / undertaking to discharge Clydesford charge | PR | Undertaking given |
| Rent deposit deeds (Units 2 and 5) — deeds of assignment | WC / PR | Engrossed |
| Apportionment account agreed (completion statement) | WC / PR | Agreed |
| Buildings insurance arranged from completion | Client | In place |
| Completion monies requisitioned from client | WC | Requested |

## D.  Completion (10 October 2025)

| Item | Who | Status |
| --- | --- | --- |
| Balance of purchase monies transferred to PR | WC | To do |
| PR confirm receipt; release of TR1, leases, deeds | PR | To do |
| Keys / managing agent handover instructions issued | PR | To do |
| Notices of assignment to tenants and managing agent | WC | To do |
| Authority to date the TR1 and rent deposit deeds | WC | To do |

## E.  Post-completion

| Item | Who | Status |
| --- | --- | --- |
| SDLT return filed and SDLT £1,077,000 paid (14 days) | WC | To do |
| Application to register transfer at HMLR (AP1) | WC | To do |
| Notice of charge discharge / title updated | WC | To do |
| Service charge retention (£18,000) held pending recon. | WC | To do |
| Completion statement and bill issued to client | WC | To do |