## Schedule of Loss
MARLDALE AGGREGATES LIMITED v CRAYFORD PLANT ENGINEERING LIMITED
SCHEDULE OF LOSS ¦ Claim No. BL-2025-LDS-000241 ¦ Prepared 4 April 2025
Ref | Head of loss / item | Basis | Qty / Days | Rate (£) | Amount (£)
A | COST OF REMEDIAL & REPLACEMENT WORKS
A1 | Hire of substitute mobile crushing spread (Sep 2024 – Feb 2025) | 22 weeks @ £18,500 | 22 | 18500
A2 | Mobilisation / demobilisation of hired plant | Lump sum | 1 | 14800 | 14800
A3 | Engineering rectification & inspection (third-party fitters) | Time & materials | 1 | 46300 | 46300
A4 | Replacement toggle assembly and bearings (interim) | Parts | 1 | 37200 | 37200
A5 | Additional fuel and consumables for hired plant | Period | 1 | 106700 | 106700
Sub-total A — Remedial & replacement
B | LOSS OF PRODUCTION & PROFIT
B1 | Lost output during 41 days of total downtime | 41 days @ 320 t/h x 8h x £4.10/t margin shortfall | 41 | 6560
B2 | Lost margin on throughput shortfall (210 vs 320 t/h) | reduced-rate period, net margin | 1 | 311640 | 311640
B3 | Bought-in finished aggregate to honour supply contracts | credit to highways contracts | 1 | 67900 | 67900
Sub-total B — Loss of production & profit
C | WASTED OVERHEADS & ABORTIVE COSTS
C1 | Standby labour during breakdowns | 41 days @ £1,420/day | 41 | 1420
C2 | Abortive haulage and rescheduling | Period | 1 | 27800 | 27800
C3 | Management time investigating failures | Estimated | 1 | 18180 | 18180
Sub-total C — Wasted overheads
TOTAL CLAIM (before interest)
Interest to date of issue (s.35A SCA 1981, ~8% simple, est.)
TOTAL INCLUDING ESTIMATED INTEREST