STATEMENT OF WORK – IMPLEMENTATION

This Statement of Work (“SOW”) is agreed under the MSSA between Meridian Signal Analytics Limited and Harcourt Beverages Group plc and governs the implementation and integration of the Cadence Platform.

- Objectives

  - To configure the Cadence Platform for Harcourt’s 32 UK production and distribution sites, integrate Harcourt’s ERP and telematics feeds, migrate historical movement data and train Authorised Users, achieving go-live by the Service Commencement Date of 5 January 2026.

- Workstreams and timeline

| Phase | Activities | Target completion |
| --- | --- | --- |
| 1. Mobilisation | Project kick-off, governance, environment provisioning | 17 October 2025 |
| 2. Integration | ERP (SAP) and telematics API connectors; data mapping | 21 November 2025 |
| 3. Data migration | Migrate 24 months of movement and inventory data | 5 December 2025 |
| 4. Configuration & UAT | Configure dashboards, alerts; user acceptance testing | 19 December 2025 |
| 5. Training & go-live | Train 60 super-users; cutover to production | 5 January 2026 |

- Customer dependencies

- Timely provision of ERP and telematics API credentials and test data.

- Nomination of a project sponsor and a technical lead with authority to make decisions.

- Availability of site data owners for two configuration workshops per region.

- Sign-off of UAT exit criteria within five business days of completion of UAT.

- Charges

  - The implementation services are delivered for the fixed implementation fee of £120,000 set out in the Order Form. Out-of-scope change requests will be estimated and agreed in writing before being undertaken, charged at £1,100 per consultant-day.

- Acceptance

  - Go-live is deemed accepted when the production environment has operated for five consecutive business days without a Severity 1 incident, or on first productive use by the Customer, whichever is earlier.