## Schedule of Loss
PENNINGTON INDUSTRIES LIMITED v CROSSFIELD ENGINEERING LIMITED
Schedule of Loss — Claim No. CC-2025-BHM-000142
Prepared by Whitfield Carter LLP ¦ Ref SW/JO/PEN-0111 ¦ Served with the Particulars of Claim, February 2025
All figures in £ sterling, exclusive of VAT. Figures drawn from the Claimant's production, purchasing and finance records.
Item | Description | Qty / basis | Unit (£) | Amount (£)
Head 1 — Cost of replacement conforming components
1 | Replacement 316L PX-440 housings — premium over original price | 4200 | 92 | 386400
2 | Alternative supplier tooling and first-article charges | lump sum |  | 48000
3 | Expedited inbound freight — first replacement batch | lump sum |  | 28000
4 | Short-lead second batch premium | 1500 | 100 | 150000
| Sub-total |  |  | 612400
Head 2 — Recall and rebuild of pumps already shipped
1 | Recall and rebuild of affected PX-series pumps (labour + parts) | 410 | 980 | 401800
2 | Customer-site field service visits | 88 | 650 | 57200
3 | Replacement seals and consumables | lump sum |  | 41900
4 | Recall logistics (collection and return) | lump sum |  | 48000
| Sub-total |  |  | 548900
Head 3 — Lost production, Assembly Line 3 (six-week shutdown)
1 | Lost contribution — Line 3 output | 6 | 105000 | 630000
2 | Idle direct labour not redeployable | 6 | 14000 | 84000
3 | Overtime to recover production backlog | lump sum |  | 28000
| Sub-total |  |  | 742000
Head 4 — Remedial inspection and rework
1 | Inspection of quarantined housing stock | 3180 | 42 | 133560
2 | Rework and scrap disposal | lump sum |  | 61040
3 | Metallurgical testing (Wraysbury and follow-up) | lump sum |  | 38000
4 | Additional QA contractor | 8 | 10750 | 86000
| Sub-total |  |  | 318600
Head 5 — Wasted management and staff time
1 | Directors' and senior management time | 220 | 140 | 30800
2 | Engineering and technical staff time | 520 | 85 | 44200
3 | Procurement, QA and administrative time | estimate |  | 21400
| Sub-total |  |  | 96400
Head 6 — Additional carriage and logistics
1 | Expedited inbound freight (replacement components) | lump sum |  | 22800
2 | Outbound carriage for rebuilt customer units | lump sum |  | 12500
3 | Courier and sample shipping to laboratory | lump sum |  | 6000
| Sub-total |  |  | 41300
| TOTAL DAMAGES CLAIMED (excluding interest) |  |  | 2359600
Interest (illustrative — to be assessed)
| Principal sum |  |  | 2359600
| Mean date of loss |  |  | 30 September 2024
| Date to which interest calculated |  |  | 9 May 2025
| Days |  |  | 221
| Rate per annum (s.35A Senior Courts Act 1981 / 4% over base) |  |  | 8%
| Interest to date of calculation |  |  | 114295.1452
| Total claim including interest to date |  |  | 2473895.1452
Note: This Schedule is provisional and is subject to revision following disclosure and expert evidence. The Claimant reserves the right to update each head of loss.