Claim No. CL-2025-000287

# Penrose Robotics Limited v Caldervale Distribution Limited

CHRONOLOGY (for Case Management Conference, 2 October 2025)

Prepared by Whitfield Carter LLP, solicitors for the Claimant. This chronology is neutral and agreed save where indicated.

| Date | Event | Ref |
| --- | --- | --- |
| 22 Jan 2024 | System Supply, Integration and Maintenance Agreement signed. Price £4,250,000. | Agreement |
| 06 Feb 2024 | Project kick-off workshop; dependencies (clause 7 / Sch 5) walked through with Mr Tovey. | MP1/12 |
| 30 Aug 2024 | 84 AMRs and infrastructure delivered to Daventry DC. Milestone 2 certified. | DN-0830 |
| 18 Sep 2024 | Caldervale supplies SKU master and slotting data. | MP1/138 |
| 20 Sep 2024 | Penrose notifies Caldervale of dimensional/weight errors in ~22% of active SKUs. | MP1/150 |
| 20 Sep 2024 | Installation complete; Milestone 3 certified (£900,000 paid). | Cert-M3 |
| 07 Oct 2024 | Phased go-live; Acceptance Period commences. | Logs |
| 09 Oct 2024 | Call re host-environment latency (31ms vs Sch 5 sub-5ms). | MP1/161 |
| 21 Oct 2024 | Caldervale launches unscheduled promotional campaign; order profile breached. | MP1/170 |
| 31 Oct 2024 | Penrose issues invoice PR-2024-0418 (Milestone 4, £1,275,000). | Inv-0418 |
| 01 Nov 2024 | Acceptance Period ends. Caldervale asserts throughput 521 u/h, availability 93.8%. | CV-rec |
| 15 Nov 2024 | Penrose issues invoice PR-2024-0427 (integration final, £162,500). | Inv-0427 |
| 07 Feb 2025 | Caldervale purports to terminate Agreement and reject System. | CV-Term |
| 24 Feb 2025 | Penrose accepts Caldervale’s repudiation. | WC-Acc |
| 10 Mar 2025 | Letter before action sent by Whitfield Carter LLP. | LBA |
| 12 May 2025 | Claim issued; Particulars of Claim served. Claim No. CL-2025-000287. | PoC |
| 09 Jul 2025 | Defence and Counterclaim served (counterclaim £2,100,000). | Def |
| 02 Oct 2025 | Case Management Conference; directions to trial. | CMC |