## Scott Schedule
PENROSE ROBOTICS LIMITED v CALDERVALE DISTRIBUTION LIMITED – SCOTT SCHEDULE
Claim No. CL-2025-000287 ¦ Sums claimed and counterclaimed ¦ Claimant's columns served 23 Jan 2026
Item | Issue / head | Claimant £ | Claimant's case | Defendant £ | Defendant's response | Court (TBC)
C1 | Unpaid Milestone 4 | 1275000 | Due as debt; no valid acceptance test occurred because Caldervale frustrated the Sch.5 conditions. |  | Not due; Milestone 4 conditional on System Acceptance which never occurred.
C2 | Unpaid integration tranche | 162500 | Due on integration sign-off, which was achieved. |  | Not due; integration not completed to standard.
C3 | Loss of maintenance revenue | 427000 | Lost five-year maintenance stream caused by Caldervale's wrongful termination. |  | Denied; termination was lawful.
C4 | Wasted / demobilisation costs | 146000 | Reasonable costs of standing down deployment team on repudiation. |  | Denied; not caused by Defendant.
D1 | Peak-season lost margin & agency labour |  | Caused by Caldervale's own data/hosting failures, not the System. | 1180000 | Lost margin and additional labour over 2024 peak due to System underperformance.
D2 | Remediation & re-slotting |  | Re-slotting reflects correction of Caldervale's own SKU data. | 265000 | Cost of remediating and re-slotting after System failure.
D3 | Replacement system procurement |  | Betterment; system was capable; mitigation unreasonable. | 655000 | Cost of procuring replacement fulfilment system.
| TOTAL CLAIM | 2010500
| TOTAL COUNTERCLAIM |  |  | 2100000