Whitfield Carter LLP

Solicitors

22 Bishopsgate, London EC2N 4BQ  |  DX 178 London City  |  +44 (0)20 7946 0822  |  www.whitfieldcarter.com

# COMPLETION CHECKLIST

Project Quartz - Acquisition of Quartz House, 14-18 Forbury Road, Reading RG1 3JH

Target completion: 15 May 2026  |  Prepared 27 April 2026 (J Osei)

| No. | Item | Responsibility | Status |
| --- | --- | --- | --- |
| 1 | Engagement letter signed and returned; AML / source of funds cleared | WC / Client | Done |
| 2 | Heads of terms agreed (subject to contract) | WC / Marlowe Greaves | Done |
| 3 | Title BK482913 investigated; official copies and plan obtained | WC | Done |
| 4 | Pre-contract searches received and reviewed (local, drainage, environmental, chancel) | WC | Done |
| 5 | CPSE.1 and property enquiries raised and satisfactory replies received | WC / Marlowe Greaves | Done |
| 6 | Leases and rent deposit deed reviewed; tenancy schedule verified | WC | Done |
| 7 | Report on title approved by client | Client | Outstanding |
| 8 | Contract approved and engrossed; parts signed | WC / Marlowe Greaves | Outstanding |
| 9 | Buyer's VAT registration and option to tax notified to HMRC and to Seller | Client / WC | Outstanding |
| 10 | Deposit of £845,000 transferred on exchange | Client / WC | Outstanding |
| 11 | Buildings insurance arranged from exchange | Client | Outstanding |
| 12 | Draft TR1 and deed of assignment of rent deposit agreed | WC / Marlowe Greaves | Outstanding |
| 13 | Completion statement agreed (apportionments + rent deposit) | WC / Marlowe Greaves | Outstanding |
| 14 | Pre-completion searches (OS1, bankruptcy / company search) carried out | WC | Outstanding |
| 15 | Completion monies remitted; keys / management information released | WC | Outstanding |
| 16 | SDLT return filed and £412,000 paid within 14 days of completion | WC | Outstanding |
| 17 | Application to register transfer at HM Land Registry (AP1) | WC | Outstanding |
| 18 | Notice of assignment of reversion served on tenants | WC | Outstanding |