PROJECT SABLE

Completion Checklist — Sable House, 40 Deansgate, Manchester (WC-00118)

Target completion: 21 November 2025

Buyer’s solicitors: Whitfield Carter LLP (ref SW/JO/WC-00118)

Seller’s solicitors: Calder Whitmore LLP (ref RPM/AS/4471)

| Ref | Item | Responsible | Status |
| --- | --- | --- | --- |
| A1 | Sale contract approved and engrossed (two parts) | Both | Complete |
| A2 | Pre-contract enquiries (CPSE.1 & CPSE.2) replied to and satisfactory | Seller | Complete |
| A3 | Title GM921044 investigated; Report on Title issued to client | Buyer | Complete |
| A4 | Search results received and reviewed (local, drainage, environmental, chancel) | Buyer | Complete |
| A5 | Occupational leases reviewed; tenancy schedule verified | Buyer | Complete |
| A6 | VAT/TOGC conditions confirmed; Buyer VAT registration & option to tax evidenced | Both | Outstanding |
| B1 | Buyer board approval to acquire obtained | Buyer | Complete |
| B2 | Funding confirmed; source of funds evidence provided (AML) | Buyer | Complete |
| B3 | Deposit (£2,475,000) ready for transfer on exchange | Buyer | Complete |
| C1 | Exchange of contracts | Both | Target 24 Oct 2025 |
| C2 | Form TR1 agreed and engrossed for execution | Both | In progress |
| C3 | Completion statement and apportionments agreed | Both | In progress |
| C4 | Tenant notices of assignment of reversion prepared | Buyer | In progress |
| C5 | Rent deposit deed (Northbridge) — deed of assignment of deposit | Seller | Outstanding |
| C6 | Undertaking for discharge of Seller’s charge (Clydesford Bank) obtained | Seller | Outstanding |
| D1 | Completion: balance of price transferred; TR1 and title documents delivered | Both | Target 21 Nov 2025 |
| D2 | SDLT return filed and SDLT (£1,227,000) paid within 14 days | Buyer | Post-completion |
| D3 | Application to register transfer at HM Land Registry (AP1) | Buyer | Post-completion |
| D4 | Tenant notices served; management/agents notified | Buyer | Post-completion |