STATEMENT OF WORKS

Project Falcon – Carrowmoor BESS (Schedule 2)

This Statement of Works forms Schedule 2 to the Energy Storage Supply, Software Licence and Long-Term Service Agreement between Verdant Energy Systems Limited and Stratton Energy plc and describes the scope, deliverables, programme and acceptance criteria for the Project.

# 1. Scope of supply

- Detailed design and engineering of the 80 MW / 160 MWh LFP battery system, power-conversion system and medium-voltage interface.

- Manufacture and factory acceptance testing (FAT) of battery enclosures and PCS units.

- Delivery to the Carrowmoor site and supervision of installation by the Customer’s civils contractor.

- Commissioning, site acceptance testing (SAT) and grid-compliance testing to the Grid Code.

- Integration of the Aeris energy-management platform and SCADA interface to the Customer’s control room.

# 2. Customer responsibilities

- Provision of the Site, civil and groundworks, access roads and laydown areas by the dates in the Project Programme.

- Procurement and energisation of the grid connection and the connection agreement with the DNO/ESO.

- Planning consent and all site permits; provision of a single point of contact for site access.

# 3. Project programme (indicative milestones)

| Milestone | Target date |
| --- | --- |
| Contract signature & advance payment | 28 November 2025 |
| Detailed design freeze | Q1 2026 |
| Cells & PCS order placed | February 2026 |
| Delivery to Site commences | Q3 2026 |
| Mechanical completion | December 2026 |
| Commissioning & SAT | Q1 2027 |
| Commercial Operation Date (target) | 31 March 2027 |

# 4. Acceptance Tests

The Acceptance Certificate will be issued when the System has: (a) passed grid-compliance testing; (b) demonstrated full-power charge and discharge at 80 MW; (c) demonstrated round-trip efficiency of at least 87% at the AC point of connection; (d) completed a 72-hour reliability run with availability of at least 98%; and (e) demonstrated Aeris dispatch with response time below 150 ms.

# 5. Deliverables and documentation

- As-built drawings, O&M manuals, FAT/SAT certificates and the grid-compliance report.

- Augmentation plan demonstrating maintenance of capacity at ≥ 70% of nameplate to year 10.

- Training of up to 8 Customer operators on Aeris and System operation.