STATEMENT OF WORK – SOW-1

Implementation & Operations – Project Lyra

Issued under the Master Software and Services Agreement between Verdant Energy Systems Limited and Pennland Water plc

Version 1.0  |  Dated 12 December 2025

1.  Purpose and scope

This SOW-1 sets out the scope, deliverables, milestones, charges and measurement-and-verification methodology for the implementation of the Aurora Grid Intelligence Platform and the managed-optimisation Services across the Customer’s 11 Sites listed in Schedule 1 to the MSSA, covering approximately 24 MW of behind-the-meter battery energy storage. Capitalised terms used but not defined here have the meanings given in the MSSA.

2.  Implementation workstreams

2.1  Discovery & baseline. Verdant will collect 12 months of half-hourly metering and energy-cost data for each Site and establish the verified energy-cost Baseline against which Energy Savings are measured.

2.2  Integration. Verdant will integrate the Platform with the Customer’s metering, SCADA and battery management systems via secure API connections, and configure dispatch and optimisation rulesets per Site.

2.3  Onboarding & testing. Verdant will onboard each Site in waves, conduct functional and security testing, and run a 30-day parallel-run before each Site goes into managed operation.

2.4  Training & go-live. Verdant will train up to 20 Authorised Users and provide go-live support.

3.  Milestones and acceptance

M1.  Project kick-off and data access established — target: Effective Date + 2 weeks.

M2.  Baseline established and signed off for all Sites — target: Effective Date + 8 weeks.

M3.  Platform integrated and first wave (4 Sites) live — target: Effective Date + 14 weeks.

M4.  All Sites integrated and in managed operation — target: Effective Date + 22 weeks.

M5.  Implementation acceptance and transition to BAU — target: Effective Date + 24 weeks.

Each milestone is subject to written acceptance by the Customer, such acceptance not to be unreasonably withheld or delayed. A milestone is deemed accepted if the Customer does not raise written, reasonable grounds for rejection within 10 business days of Verdant’s notice of completion.

4.  Measurement & verification (M&V)

Energy Savings are calculated monthly as the difference between (a) the Baseline-adjusted expected energy cost for the relevant Sites, normalised for production volume, weather and tariff changes using the IPMVP Option C (whole-facility) methodology, and (b) the actual energy cost incurred. Verified annual Energy Savings drive the 18% shared-savings fee in Schedule 2 of the MSSA.

5.  Charges specific to SOW-1

Implementation fee: £185,000 (excl. VAT), invoiced in two equal instalments of £92,500 at kick-off (M1) and on implementation acceptance (M5). Ongoing Platform subscription (£312,000 p.a.) and managed-optimisation charges (£96,000 p.a.) are as set out in Schedule 2 of the MSSA and are not duplicated here.

6.  Customer dependencies

The Customer will provide: timely access to metering and SCADA data; safe site access for commissioning; a nominated project sponsor and technical point of contact; and approval of dispatch parameters that affect site operations. Delay in meeting these dependencies may extend the milestone dates accordingly.

Agreed for and on behalf of the Parties:

Verdant: ..................   Marcus Calder, Chief Technology Officer

Pennland: ..................   Daniel Pryce, Head of Energy & Net Zero