Claim No. HT-2026-000087

VERDANT ENERGY SYSTEMS LIMITED v CALDERHALL CELLS LIMITED

CHRONOLOGY

This chronology is prepared by the Claimant for the case management conference. It is non-contentious save where indicated and is without prejudice to the Claimant’s pleaded case.

| Date | Event | Ref |
| --- | --- | --- |
| 18 Mar 2024 | Technical qualification workshop; Verdant informs Calderhall of energisation deadline and availability-revenue requirements. | MC1/12 |
| 22 May 2024 | Cell Supply Agreement executed (3 strings; £2,940,000). | MC1/1 |
| 19 Aug 2024 | String A delivered to Brackmoor site. | MC1/41 |
| 9 Sep 2024 | String B delivered to Brackmoor site. | MC1/43 |
| 26 Sep 2024 | String C delivered to Brackmoor site. | MC1/45 |
| 14 Oct 2024 | Final instalment of price paid (£2,940,000 in full). | MC1/52 |
| 4 Nov 2024 | Energisation and commissioning of facility commences. | MC1/58 |
| 11–22 Nov 2024 | Capacity-characterisation testing; String B exhibits accelerated fade, voltage divergence and localised heating. | MC1/61 |
| 22 Nov 2024 | Verdant suspends commissioning of String B. | MC1/70 |
| 25 Nov 2024 | Verdant notifies Calderhall of non-conformities under clause 9. | MC1/72 |
| 3 Dec 2024 | Joint site inspection of String B. | MC1/78 |
| 13 Dec 2024 | Contractual energisation date (missed). | MC1/80 |
| 24 Jan 2025 | Wraysbury Materials Laboratory failure-analysis report served. | MC1/95 |
| 7 Feb 2025 | Letter before action sent to Calderhall. | MC1/130 |
| 28 Feb 2025 | Calderhall’s solicitors deny liability. | MC1/138 |
| c. 7 Feb 2025 | Facility energised (≈ 8 weeks late) following remediation. | MC1/142 |
| 12 May 2025 | Claim Form and Particulars of Claim issued. | — |
| 18 Jun 2025 | Defence served. | — |
| 8 Oct 2025 | Case Management Conference; directions to trial. | — |