## Schedule of Loss
Verdant Energy Systems Ltd v Calderhall Cells Ltd
Claim No. HT-2026-000087 · Schedule of Loss · Served 12 May 2025 · All figures £ exclusive of VAT
Item | Head of loss | Basis / narrative | Quantity / basis | Unit (£) | Amount (£)
1 | Replacement cells and modules (String B) | Purchase of replacement LFP cells and 28 replacement modules from alternative qualified supplier (Northvale Cells Ltd) | 28 | 36250 | 1015000
2 | Removal and reinstallation labour | Removal of defective String B modules, reinstallation of replacements, recommissioning labour (1,400 hrs) | 1 | 268400 | 268400
3 | Failure investigation and testing | Wraysbury Materials Laboratory destructive/non-destructive analysis and report (24 Jan 2025) plus screening of Strings A & C | 1 | 74600 | 74600
4 | Extended preliminaries (commissioning delay) | Site preliminaries, plant hire, supervision and standby for 8-week delay period | 8 | 24150 | 193200
5 | Liquidated damages paid to EPC counterparty | LDs paid to Halloway Renewables Ltd under EPC contract for late energisation (£80,000/week × 8 weeks) | 8 | 80000 | 640000
6 | Lost availability revenue | Net availability / capacity-market revenue forgone during 8-week delay | 8 | 35500 | 284000
| TOTAL CLAIM |  |  |  | 2475200
Interest (s.35A Senior Courts Act 1981) claimed at 4% over base from dates loss incurred to judgment — to be computed.
Note: liability cap (clause 11) and exclusion of consequential loss are in issue; items 5 and 6 are pleaded as direct losses.