WEXFORD CONSUMER BRANDS LIMITED v PINNACLE SYSTEMS LIMITED

Claim No. CC-2025-LON-000512

CHRONOLOGY

Prepared by Whitfield Carter LLP. Working document — for internal use and case management.

| Date | Event | Reference |
| --- | --- | --- |
| 26 Jan 2024 | Statement of Requirements agreed and signed off by both parties. | C/14 |
| 19 Feb 2024 | Solution Design Document agreed. | C/41 |
| 4 Mar 2024 | Implementation Agreement executed (charges £1,840,000 + VAT). | C/1 |
| 1 Apr 2024 | Project mobilisation; design workshops commence. | C/88 |
| 30 Jun 2024 | Contractual deadline for Claimant master data (per Schedule 4). | C/3 |
| 19 Jul 2024 | Defendant Highlight Report raises data quality / SME availability. | D/22 |
| 23 Aug 2024 | Further Highlight Report repeats data and process-change concerns. | D/29 |
| 28 Aug 2024 | UAT cycle 1: System fails 41 of 96 critical scripts. Project Board. | C/112 |
| 9 Sep 2024 | Claimant master data finally delivered in usable form. | D/34 |
| 30 Oct 2024 | Project sponsor approves Banbury go-live in writing. | D/51 |
| 4 Nov 2024 | Banbury technical go-live; stock records corrupted; despatch halts. | C/130 |
| 4–12 Nov 2024 | Despatch from Banbury halted for nine days; manual operation. | C/131 |
| 18 Nov 2024 | Claimant suspends rollout to Wakefield and Avonmouth. | C/140 |
| 24 Jan 2025 | Claimant terminates the Agreement for repudiatory breach. | C/150 |
| 31 Jan 2025 | Defendant purports to accept Claimant’s alleged repudiation. | D/60 |
| 12 Feb 2025 | Letter of Claim sent. | C/160 |
| 12 Mar 2025 | Defendant’s response to Letter of Claim (liability denied). | D/70 |
| 11 Apr 2025 | Claim Form and Particulars of Claim issued. | C/170 |
| 6 Jun 2025 | Defence and Counterclaim served. | D/80 |
| 4 Jul 2025 | Reply and Defence to Counterclaim served. | C/185 |
| 18 Sep 2025 | Costs and Case Management Conference; directions ordered. | C/200 |